## Version 2
Project Development and Completion Tracker
Porject ID: 14
Project Start Date: 10-08-2023 Project End Date: 25-11-2023
Porject Descreption: Develop an accurate and adaptable hate speech detection system capable of identifying offensive and discriminatory language in real-time online textual content.
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members | Shivam Khode |  | Project Development Student Team Memebers | Shivam Khode |  | Team Lead | Project Domain Expert Team Members (Geolife)
| Omkar More |  |  |  |  | Frond End
| Mayank Modi |  |  | Omkar More |  | Team Lead
Front/Back End
|  |  |  | Mayank Modi |  | Team Lead
Back End
Front End
Epic: | As a user, Ishould need a safe and inclusive online environment.
Story 1: | As a user , I should able to report hate speech promptly.
Story 2: | As a user , I should able to Block or mute offensive users.
Story 3: | As a user, My privacy should be protected when reporting hate speech or engaging in content moderation.
Task1: | Design a layout for Object related mapping
Task2: | Design a layout to find database.
Task3: | Design a layout of Hate Speech Detection Integration:
Task4: | Design layout to find accuracy percentage of hate speech.
Task5: | Design a layout to predict Data of hate speech.
Acceptance Criteria:
1 | The hate speech detection system should achieve a high level of accuracy, with a focus on reducing false positives.
2 | The system should be capable of detecting hate speech in various languages and contexts.
3 | Performance metrics should be regularly monitored, and thresholds for action should be defined.
4 | The system should be updated and improved iteratively based on real-world feedback and changing hate speech patterns.
5 | Compliance with legal and regulatory requirements should be maintained throughout the project.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 1 | Design a layout for Object related mapping | Design a system for accessing database and getting accurate information from it. | Complete | Shivam khode | 2023-08-08 |  |  | 19-08-2023 | 100% | Not Started | Medium
|  | Design service that can use database as an object for further clarification. | Complete | Shivam khode | 2023-08-21 |  |  | 02-09-2023 | 100%
| Design a layout to find database. | Choose a database system for detecting hate speech. | Complete | Omkar more | 2023-09-04 |  |  | 16-09-2023 | 100% | In Progress | Low
|  | Design database to handle content submissions, detection results. | Complete | Omkar more | 2023-09-18 |  |  | 30-09-2023 | 100%
| Design a layout of Hate Speech Detection Integration: | Develop an service to analyze user-submitted content for hate speech. | Complete | Shivam khode,Omkar more | 2023-10-02 |  |  | 25-10-2023 | 100% | Complete | High
|  | Implement mechanisms to continuously update and improve the detection | Complete | Shivam khode,Omkar more | 2023-10-28 |  |  | 01-11-2023 | 100%
| Design layout to find accuracy percentage of hate speech. | Develop a service to find the accuracy percentage of hate speech. | Complete | Mayank modi | 2023-11-01 |  |  | 10-11-2023 | 100%
On Hold
| Design a layout to predict Data of hate speech. | Develop a database to find the speech is “Hate Speech”, "Offensive Speech", "No Hate and Offensive Speech. | Complete | Mayank modi | 2023-11-21 |  |  | 25-11-2023 | 100% | Overdue